## Summary
Schedule: | SL-DEMO | Data Date: | 2026-01-05 | Project Start: | 2026-01-05 | Project Finish: | 2028-06-08
Severity | Check | Finding | Count | Reference
info | calendars | 1 calendars in use | 0 | AACE RP 29R-03 §2; PMI Practice Standard §3.1.2.6; PMBOK §2.3; CIOB Guide §4.13
info | constraints | 3 constrained activities | 0 | DCMA 14-Point §5; AACE RP 29R-03 §2; SCL Protocol §1; PMI Practice Standard §3.4.6; PMBOK §2.3; CIOB Guide §4.27
info | critical_path | CPLI = 1.00 | 0 | DCMA 14-Point §11/§13; AACE RP 29R-03 §4.3; PMI Practice Standard §3.4.1; PMBOK §2.3; CIOB Guide §4.29
info | durations | 1 activities with duration over 44 days | 1 | DCMA 14-Point §8; PMI Practice Standard §3.2.1.5; CIOB Guide §4.2, §4.19
info | float_analysis | Float distribution | 0 | DCMA 14-Point §6/§7; AACE RP 29R-03 §4.3; PMI Practice Standard §3.4.2; PMBOK §2.3; CIOB Guide §4.28
warning | float_analysis | 58 activities with float over 44 days | 58 | DCMA 14-Point §6/§7; AACE RP 29R-03 §4.3; PMI Practice Standard §3.4.2; PMBOK §2.3; CIOB Guide §4.28
info | float_analysis | 16 near-critical activities | 16 | DCMA 14-Point §6/§7; AACE RP 29R-03 §4.3; PMI Practice Standard §3.4.2; PMBOK §2.3; CIOB Guide §4.28
info | redundant_logic | 4 potentially redundant relationships | 0 | AACE RP 29R-03 §2; PMI Practice Standard §3.4.7
warning | dangling_logic | 12 activities with dangling logic | 12 | AACE RP 29R-03 §2; PMI Practice Standard §3.4.7
info | open_ends | 1 activities with no predecessor | 1 | DCMA 14-Point §1; AACE RP 29R-03 §2; PMI Practice Standard §3.4.7; CIOB Guide §4.23.1
info | open_ends | 6 activities with no successor | 6 | DCMA 14-Point §1; AACE RP 29R-03 §2; PMI Practice Standard §3.4.7; CIOB Guide §4.23.1
info | relationship_types | Relationship type distribution | 0 | DCMA 14-Point §2/§3/§4; AACE RP 29R-03 §2; PMI Practice Standard §3.2.1.3; §3.4.9; §3.4.10; CIOB Guide §4.25, §4.26
warning | relationship_types | 9 relationships with positive lag | 0 | DCMA 14-Point §2/§3/§4; AACE RP 29R-03 §2; PMI Practice Standard §3.2.1.3; §3.4.9; §3.4.10; CIOB Guide §4.25, §4.26
info | scheduling_options | Schedule calculated under Retained Logic | 0 | AACE RP 29R-03 §3.3.D; SCL Protocol §11; CIOB Guide §4.30.7.39
info | scheduling_options | Total float calculated using finish float | 0 | AACE RP 29R-03 §3.3.D; SCL Protocol §11; CIOB Guide §4.30.7.39

## Key Milestones
Milestone | Activity ID | WBS | Planned Start | Planned Finish | Actual Start | Actual Finish | Progress % | On Critical Path | Detection Reason
Substructure complete | MS-SUB-END | W20 | 2026-09-29 | 2026-09-29 |  |  | 0 | Yes | finish milestone on critical path (terminal in WBS package)
Fit-out complete | MS-FIT-END | W60 | 2028-03-07 | 2028-03-07 |  |  | 0 | Yes | finish milestone on critical path (terminal in WBS package)
Practical Completion | MS-PC | W83 | 2028-06-08 | 2028-06-08 |  |  | 0 | Yes | contractual milestone — matched 'practical completion'

## Critical Path
Activity ID | Activity Name | WBS | Duration (wd) | Remaining (wd) | Planned Start | Planned Finish | Actual Start | Actual Finish | Total Float (wd) | Complete | Calendar
MS-START | Project Start | W10 | 0 | 0 | 2026-01-05 | 2026-01-05 |  |  | 0 | No | Standard 5-day
PRE-110 | Submit planning permission application | W11 | 5 | 5 | 2026-01-05 | 2026-01-12 |  |  | 0 | No | Standard 5-day
PRE-120 | Planning permission approval | W11 | 25 | 25 | 2026-01-12 | 2026-02-16 |  |  | 0 | No | Standard 5-day
PRE-130 | Building control submission | W11 | 10 | 10 | 2026-02-16 | 2026-03-02 |  |  | 0 | No | Standard 5-day
PRE-140 | Building control approval | W11 | 15 | 15 | 2026-03-02 | 2026-03-23 |  |  | 0 | No | Standard 5-day
SUB-110 | Bulk excavation Zone A | W21 | 12 | 12 | 2026-03-23 | 2026-04-10 |  |  | 0 | No | Standard 5-day
SUB-210 | Piling rig mobilisation | W22 | 4 | 4 | 2026-04-10 | 2026-04-16 |  |  | 0 | No | Standard 5-day
SUB-220 | CFA piling Zone A | W22 | 18 | 18 | 2026-04-16 | 2026-05-13 |  |  | 0 | No | Standard 5-day
SUB-230 | CFA piling Zone B | W22 | 18 | 18 | 2026-05-13 | 2026-06-08 |  |  | 0 | No | Standard 5-day
SUB-240 | Pile integrity testing | W22 | 6 | 6 | 2026-06-08 | 2026-06-16 |  |  | 0 | No | Standard 5-day
SUB-250 | Pile trimming | W22 | 8 | 8 | 2026-06-16 | 2026-06-26 |  |  | 0 | No | Standard 5-day
SUB-310 | Pile cap excavation | W23 | 8 | 8 | 2026-06-26 | 2026-07-08 |  |  | 0 | No | Standard 5-day
SUB-320 | Pile cap reinforcement | W23 | 10 | 10 | 2026-07-08 | 2026-07-22 |  |  | 0 | No | Standard 5-day
SUB-330 | Pile cap concrete pour | W23 | 6 | 6 | 2026-07-22 | 2026-07-30 |  |  | 0 | No | Standard 5-day
SUB-340 | Ground beam install | W23 | 12 | 12 | 2026-07-30 | 2026-08-17 |  |  | 0 | No | Standard 5-day
SUB-410 | Basement slab formwork | W24 | 8 | 8 | 2026-08-17 | 2026-08-27 |  |  | 0 | No | Standard 5-day
SUB-420 | Basement slab reinforcement | W24 | 12 | 12 | 2026-08-27 | 2026-09-15 |  |  | 0 | No | Standard 5-day
SUB-430 | Basement slab waterproofing | W24 | 6 | 6 | 2026-09-09 | 2026-09-17 |  |  | 0 | No | Standard 5-day
SUB-440 | Basement slab pour | W24 | 8 | 8 | 2026-09-17 | 2026-09-29 |  |  | 0 | No | Standard 5-day
MS-SUB-END | Substructure complete | W20 | 0 | 0 | 2026-09-29 | 2026-09-29 |  |  | 0 | No | Standard 5-day
SUP-110 | Column starter bars L1 | W31 | 4 | 4 | 2026-09-29 | 2026-10-05 |  |  | 0 | No | Standard 5-day
SUP-120 | Column formwork L1 | W31 | 6 | 6 | 2026-10-05 | 2026-10-13 |  |  | 0 | No | Standard 5-day
SUP-130 | Column pour L1 | W31 | 4 | 4 | 2026-10-13 | 2026-10-19 |  |  | 0 | No | Standard 5-day
SUP-140 | Column starter bars L2 | W31 | 4 | 4 | 2026-10-19 | 2026-10-23 |  |  | 0 | No | Standard 5-day
SUP-150 | Column formwork L2 | W31 | 6 | 6 | 2026-10-23 | 2026-11-02 |  |  | 0 | No | Standard 5-day
SUP-160 | Column pour L2 | W31 | 4 | 4 | 2026-11-02 | 2026-11-06 |  |  | 0 | No | Standard 5-day
SUP-210 | Column starter bars L3 | W31 | 4 | 4 | 2026-11-10 | 2026-11-16 |  |  | 0 | No | Standard 5-day
SUP-220 | Column formwork L3 | W31 | 6 | 6 | 2026-11-16 | 2026-11-24 |  |  | 0 | No | Standard 5-day
SUP-230 | Column pour L3 | W31 | 4 | 4 | 2026-11-24 | 2026-11-30 |  |  | 0 | No | Standard 5-day
SUP-240 | Column starter bars L4 | W32 | 4 | 4 | 2026-12-02 | 2026-12-08 |  |  | 0 | No | Standard 5-day
SUP-250 | Column formwork L4 | W32 | 6 | 6 | 2026-12-08 | 2026-12-16 |  |  | 0 | No | Standard 5-day
SUP-260 | Column pour L4 | W32 | 4 | 4 | 2026-12-16 | 2026-12-22 |  |  | 0 | No | Standard 5-day
SUP-440 | Slab L4 formwork | W34 | 8 | 8 | 2027-01-04 | 2027-01-14 |  |  | 0 | No | Standard 5-day
SUP-450 | Slab L4 reinforcement | W34 | 8 | 8 | 2027-01-14 | 2027-01-26 |  |  | 0 | No | Standard 5-day
SUP-460 | Slab L4 pour | W34 | 6 | 6 | 2027-01-26 | 2027-02-03 |  |  | 0 | No | Standard 5-day
MEP-130 | Electrical containment L4-L6 | W51 | 18 | 18 | 2027-04-09 | 2027-05-06 |  |  | 0 | No | Standard 5-day
MEP-140 | Cable pulling L1-L3 | W51 | 20 | 20 | 2027-05-06 | 2027-06-03 |  |  | 0 | No | Standard 5-day
MEP-150 | Cable pulling L4-L6 | W51 | 20 | 20 | 2027-06-03 | 2027-07-01 |  |  | 0 | No | Standard 5-day
MEP-160 | Distribution boards | W51 | 12 | 12 | 2027-07-01 | 2027-07-19 |  |  | 0 | No | Standard 5-day
MEP-170 | Lighting wiring rough-in | W51 | 18 | 18 | 2027-07-19 | 2027-08-12 |  |  | 0 | No | Standard 5-day
MEP-180 | Power outlet rough-in | W51 | 18 | 18 | 2027-08-12 | 2027-09-08 |  |  | 0 | No | Standard 5-day
FIT-110 | Stud partition L1 | W61 | 12 | 12 | 2027-08-16 | 2027-09-02 |  |  | 0 | No | Standard 5-day
FIT-120 | Stud partition L2 | W61 | 12 | 12 | 2027-08-24 | 2027-09-10 |  |  | 0 | No | Standard 5-day
FIT-130 | Stud partition L3 | W61 | 12 | 12 | 2027-09-02 | 2027-09-20 |  |  | 0 | No | Standard 5-day
FIT-140 | Stud partition L4 | W61 | 12 | 12 | 2027-09-10 | 2027-09-28 |  |  | 0 | No | Standard 5-day
FIT-150 | Stud partition L5-L6 | W61 | 18 | 18 | 2027-09-20 | 2027-10-14 |  |  | 0 | No | Standard 5-day
FIT-160 | Suspended ceilings L1-L3 | W61 | 25 | 25 | 2027-09-20 | 2027-10-25 |  |  | 0 | No | Standard 5-day
FIT-210 | Plastering L1-L3 | W62 | 20 | 20 | 2027-10-06 | 2027-11-03 |  |  | 0 | No | Standard 5-day
FIT-170 | Suspended ceilings L4-L6 | W61 | 25 | 25 | 2027-10-14 | 2027-11-18 |  |  | 0 | No | Standard 5-day
FIT-180 | Ceiling integration MEP | W61 | 12 | 12 | 2027-10-25 | 2027-11-10 |  |  | 0 | No | Standard 5-day
FIT-220 | Plastering L4-L6 | W62 | 20 | 20 | 2027-11-03 | 2027-12-01 |  |  | 0 | No | Standard 5-day
FIT-240 | Painting L4-L6 | W62 | 18 | 18 | 2027-12-01 | 2027-12-29 |  |  | 0 | No | Standard 5-day
FIT-260 | Floor finishes L4-L6 | W62 | 22 | 22 | 2027-12-29 | 2028-01-28 |  |  | 0 | No | Standard 5-day
FIT-310 | Reception joinery | W63 | 15 | 15 | 2028-01-06 | 2028-01-27 |  |  | 0 | No | Standard 5-day
FIT-320 | Toilet vanity install | W63 | 18 | 18 | 2028-01-06 | 2028-02-01 |  |  | 0 | No | Standard 5-day
FIT-330 | Tea-point joinery | W63 | 12 | 12 | 2028-01-13 | 2028-01-31 |  |  | 0 | No | Standard 5-day
FIT-340 | Meeting room joinery | W63 | 18 | 18 | 2028-01-20 | 2028-02-15 |  |  | 0 | No | Standard 5-day
FIT-350 | Built-in storage and fittings | W63 | 15 | 15 | 2028-02-03 | 2028-02-24 |  |  | 0 | No | Standard 5-day
FIT-360 | Final joinery snagging | W63 | 8 | 8 | 2028-02-24 | 2028-03-07 |  |  | 0 | No | Standard 5-day
MS-FIT-END | Fit-out complete | W60 | 0 | 0 | 2028-03-07 | 2028-03-07 |  |  | 0 | No | Standard 5-day
CMS-210 | Client walkthrough and snag list | W82 | 5 | 5 | 2028-04-18 | 2028-04-25 |  |  | 0 | No | Standard 5-day
CMS-220 | Major snags rectification | W82 | 15 | 15 | 2028-04-25 | 2028-05-16 |  |  | 0 | No | Standard 5-day
CMS-230 | Minor snags rectification | W82 | 12 | 12 | 2028-05-04 | 2028-05-22 |  |  | 0 | No | Standard 5-day
CMS-240 | Final inspection | W82 | 4 | 4 | 2028-05-16 | 2028-05-22 |  |  | 0 | No | Standard 5-day
CMS-310 | Building handover documentation | W83 | 8 | 8 | 2028-05-18 | 2028-05-30 |  |  | 0 | No | Standard 5-day
CMS-320 | O&M manuals issued | W83 | 4 | 4 | 2028-05-30 | 2028-06-05 |  |  | 0 | No | Standard 5-day
CMS-330 | Soft landings start | W83 | 3 | 3 | 2028-06-05 | 2028-06-08 |  |  | 0 | No | Standard 5-day
MS-PC | Practical Completion | W83 | 0 | 0 | 2028-06-08 | 2028-06-08 |  |  | 0 | No | Standard 5-day

## Activities
Activity ID | Activity Name | WBS | Type | Duration (wd) | Remaining (wd) | Planned Start | Planned Finish | Actual Start | Actual Finish | Total Float (wd) | Free Float (wd) | Critical | Complete | Calendar | Constraint | Predecessors | Successors
MS-START | Project Start | W10 | start_milestone | 0 | 0 | 2026-01-05 | 2026-01-05 |  |  | 0 | 0 | Yes | No | Standard 5-day | SO |  | PRE-110 (FS), PRE-310 (FS)
PRE-110 | Submit planning permission application | W11 | task | 5 | 5 | 2026-01-05 | 2026-01-12 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | MS-START (FS) | PRE-120 (FS), PRE-210 (FS+20d), PRE-310 (FS)
PRE-120 | Planning permission approval | W11 | task | 25 | 25 | 2026-01-12 | 2026-02-16 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | PRE-110 (FS) | PRE-130 (FS)
PRE-130 | Building control submission | W11 | task | 10 | 10 | 2026-02-16 | 2026-03-02 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | PRE-120 (FS) | PRE-140 (FS)
PRE-140 | Building control approval | W11 | task | 15 | 15 | 2026-03-02 | 2026-03-23 |  |  | 0 | 0 | Yes | No | Standard 5-day | SNLT | PRE-130 (FS) | SUB-110 (FS)
PRE-210 | Site mobilisation | W12 | task | 8 | 8 | 2026-02-09 | 2026-02-19 |  |  | 7 | 0 | No | No | Standard 5-day |  | PRE-110 (FS+20d) | PRE-220 (FS), PRE-230 (FS)
PRE-220 | Site hoarding and access | W12 | task | 5 | 5 | 2026-02-19 | 2026-02-26 |  |  | 7 | 0 | No | No | Standard 5-day |  | PRE-210 (FS) | PRE-240 (FS)
PRE-230 | Welfare cabins and offices | W12 | task | 7 | 7 | 2026-02-19 | 2026-03-02 |  |  | 648 | 0 | No | No | Standard 5-day |  | PRE-210 (FS)
PRE-240 | Temporary services connection | W12 | task | 6 | 6 | 2026-02-26 | 2026-03-06 |  |  | 7 | 0 | No | No | Standard 5-day |  | PRE-220 (FS) | PRE-250 (FS)
PRE-250 | Site security and CCTV | W12 | task | 4 | 4 | 2026-03-06 | 2026-03-12 |  |  | 7 | 0 | No | No | Standard 5-day |  | PRE-240 (FS) | SUB-110 (FS)
PRE-310 | Topographical survey | W13 | task | 4 | 4 | 2026-01-12 | 2026-01-16 |  |  | 28 | 0 | No | No | Standard 5-day |  | MS-START (FS), PRE-110 (FS) | PRE-320 (FS)
PRE-320 | Geotechnical investigation | W13 | task | 12 | 12 | 2026-01-16 | 2026-02-03 |  |  | 28 | 0 | No | No | Standard 5-day |  | PRE-310 (FS) | PRE-330 (FS)
PRE-330 | Utilities survey | W13 | task | 6 | 6 | 2026-02-03 | 2026-02-11 |  |  | 28 | 0 | No | No | Standard 5-day |  | PRE-320 (FS) | SUB-110 (FS)
SUB-110 | Bulk excavation Zone A | W21 | task | 12 | 12 | 2026-03-23 | 2026-04-10 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | PRE-140 (FS), PRE-250 (FS), PRE-330 (FS) | SUB-120 (SS+5d), SUB-140 (FS), SUB-210 (FS)
SUB-120 | Bulk excavation Zone B | W21 | task | 12 | 12 | 2026-03-30 | 2026-04-17 |  |  | 36 | 0 | No | No | Standard 5-day |  | SUB-110 (SS+5d) | SUB-130 (FS)
SUB-130 | Trim and dewater | W21 | task | 8 | 8 | 2026-04-17 | 2026-04-29 |  |  | 36 | 0 | No | No | Standard 5-day |  | SUB-120 (FS) | SUB-140 (FS)
SUB-140 | Blinding to formation level | W21 | task | 5 | 5 | 2026-04-29 | 2026-05-07 |  |  | 36 | 0 | No | No | Standard 5-day |  | SUB-110 (FS), SUB-130 (FS) | SUB-310 (FS)
SUB-210 | Piling rig mobilisation | W22 | task | 4 | 4 | 2026-04-10 | 2026-04-16 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-110 (FS) | SUB-220 (FS)
SUB-220 | CFA piling Zone A | W22 | task | 18 | 18 | 2026-04-16 | 2026-05-13 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-210 (FS) | SUB-230 (FS), SUB-250 (FS)
SUB-230 | CFA piling Zone B | W22 | task | 18 | 18 | 2026-05-13 | 2026-06-08 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-220 (FS) | SUB-240 (FS)
SUB-240 | Pile integrity testing | W22 | task | 6 | 6 | 2026-06-08 | 2026-06-16 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-230 (FS) | SUB-250 (FS)
SUB-250 | Pile trimming | W22 | task | 8 | 8 | 2026-06-16 | 2026-06-26 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-220 (FS), SUB-240 (FS) | SUB-310 (FS)
SUB-310 | Pile cap excavation | W23 | task | 8 | 8 | 2026-06-26 | 2026-07-08 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-140 (FS), SUB-250 (FS) | MEP-310 (FS), SUB-320 (FS)
SUB-320 | Pile cap reinforcement | W23 | task | 10 | 10 | 2026-07-08 | 2026-07-22 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-310 (FS) | SUB-330 (FS)
SUB-330 | Pile cap concrete pour | W23 | task | 6 | 6 | 2026-07-22 | 2026-07-30 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-320 (FS) | SUB-340 (FS)
SUB-340 | Ground beam install | W23 | task | 12 | 12 | 2026-07-30 | 2026-08-17 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-330 (FS) | SUB-410 (FS)
SUB-410 | Basement slab formwork | W24 | task | 8 | 8 | 2026-08-17 | 2026-08-27 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-340 (FS) | SUB-420 (FS)
SUB-420 | Basement slab reinforcement | W24 | task | 12 | 12 | 2026-08-27 | 2026-09-15 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-410 (FS) | SUB-430 (FS)
SUB-430 | Basement slab waterproofing | W24 | task | 6 | 6 | 2026-09-09 | 2026-09-17 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-420 (FS) | SUB-440 (FS)
SUB-440 | Basement slab pour | W24 | task | 8 | 8 | 2026-09-17 | 2026-09-29 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-430 (FS) | MS-SUB-END (FS)
MS-SUB-END | Substructure complete | W20 | finish_milestone | 0 | 0 | 2026-09-29 | 2026-09-29 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUB-440 (FS) | MEP-110 (FS), SUP-110 (FS)
SUP-110 | Column starter bars L1 | W31 | task | 4 | 4 | 2026-09-29 | 2026-10-05 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | MS-SUB-END (FS) | SUP-120 (FS), SUP-130 (FS)
SUP-120 | Column formwork L1 | W31 | task | 6 | 6 | 2026-10-05 | 2026-10-13 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-110 (FS) | SUP-130 (FS)
SUP-130 | Column pour L1 | W31 | task | 4 | 4 | 2026-10-13 | 2026-10-19 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-110 (FS), SUP-120 (FS) | SUP-140 (FS), SUP-310 (FS)
SUP-140 | Column starter bars L2 | W31 | task | 4 | 4 | 2026-10-19 | 2026-10-23 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-130 (FS) | SUP-150 (FS)
SUP-150 | Column formwork L2 | W31 | task | 6 | 6 | 2026-10-23 | 2026-11-02 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-140 (FS) | SUP-160 (FS)
SUP-160 | Column pour L2 | W31 | task | 4 | 4 | 2026-11-02 | 2026-11-06 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-150 (FS) | ENV-110 (FS), MEP-210 (FS), MEP-320 (FS), SUP-210 (FS), SUP-340 (FS)
SUP-310 | Slab L1 formwork | W33 | task | 8 | 8 | 2026-10-13 | 2026-10-23 |  |  | 461 | 0 | No | No | Standard 5-day |  | SUP-130 (FS) | SUP-320 (FS)
SUP-320 | Slab L1 reinforcement | W33 | task | 8 | 8 | 2026-10-23 | 2026-11-04 |  |  | 461 | 0 | No | No | Standard 5-day |  | SUP-310 (FS) | SUP-330 (FS)
SUP-330 | Slab L1 pour | W33 | task | 6 | 6 | 2026-11-04 | 2026-11-12 |  |  | 461 | 0 | No | No | Standard 5-day |  | SUP-320 (FS)
SUP-340 | Slab L2 formwork | W33 | task | 8 | 8 | 2026-11-06 | 2026-11-18 |  |  | 10 | 0 | No | No | Standard 5-day |  | SUP-160 (FS) | SUP-350 (FS)
SUP-350 | Slab L2 reinforcement | W33 | task | 8 | 8 | 2026-11-18 | 2026-11-30 |  |  | 10 | 0 | No | No | Standard 5-day |  | SUP-340 (FS) | SUP-360 (FS)
SUP-360 | Slab L2 pour | W33 | task | 6 | 6 | 2026-11-30 | 2026-12-08 |  |  | 10 | 0 | No | No | Standard 5-day |  | SUP-350 (FS) | MEP-120 (FS), SUP-410 (FS)
SUP-210 | Column starter bars L3 | W31 | task | 4 | 4 | 2026-11-10 | 2026-11-16 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-160 (FS) | SUP-220 (FS)
SUP-220 | Column formwork L3 | W31 | task | 6 | 6 | 2026-11-16 | 2026-11-24 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-210 (FS) | SUP-230 (FS)
SUP-230 | Column pour L3 | W31 | task | 4 | 4 | 2026-11-24 | 2026-11-30 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-220 (FS) | SUP-240 (FS), SUP-410 (FS)
SUP-240 | Column starter bars L4 | W32 | task | 4 | 4 | 2026-12-02 | 2026-12-08 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-230 (FS) | SUP-250 (FS)
SUP-250 | Column formwork L4 | W32 | task | 6 | 6 | 2026-12-08 | 2026-12-16 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-240 (FS) | SUP-260 (FS)
SUP-260 | Column pour L4 | W32 | task | 4 | 4 | 2026-12-16 | 2026-12-22 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-250 (FS) | SUP-440 (FS)
SUP-410 | Slab L3 formwork | W34 | task | 8 | 8 | 2026-11-30 | 2026-12-10 |  |  | 425 | 0 | No | No | Standard 5-day |  | SUP-230 (FS), SUP-360 (FS) | SUP-420 (FS)
SUP-420 | Slab L3 reinforcement | W34 | task | 8 | 8 | 2026-12-10 | 2026-12-22 |  |  | 425 | 0 | No | No | Standard 5-day |  | SUP-410 (FS) | SUP-430 (FS)
SUP-430 | Slab L3 pour | W34 | task | 6 | 6 | 2026-12-22 | 2027-01-04 |  |  | 425 | 0 | No | No | Standard 5-day |  | SUP-420 (FS)
SUP-440 | Slab L4 formwork | W34 | task | 8 | 8 | 2027-01-04 | 2027-01-14 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-260 (FS) | SUP-450 (FS)
SUP-450 | Slab L4 reinforcement | W34 | task | 8 | 8 | 2027-01-14 | 2027-01-26 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-440 (FS) | SUP-460 (FS)
SUP-460 | Slab L4 pour | W34 | task | 6 | 6 | 2027-01-26 | 2027-02-03 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | SUP-450 (FS) | MEP-130 (FS), SUP-510 (FS)
SUP-510 | Roof slab formwork | W35 | task | 10 | 10 | 2027-02-03 | 2027-02-17 |  |  | 206 | 0 | No | No | Standard 5-day |  | SUP-460 (FS) | SUP-520 (FS)
SUP-520 | Roof slab reinforcement | W35 | task | 8 | 8 | 2027-02-17 | 2027-03-01 |  |  | 206 | 0 | No | No | Standard 5-day |  | SUP-510 (FS) | SUP-530 (FS)
SUP-530 | Roof slab pour | W35 | task | 6 | 6 | 2027-03-01 | 2027-03-09 |  |  | 206 | 0 | No | No | Standard 5-day |  | SUP-520 (FS) | ENV-140 (FS), SUP-610 (FS)
SUP-610 | Roof waterproofing membrane | W36 | task | 8 | 8 | 2027-03-09 | 2027-03-19 |  |  | 381 | 0 | No | No | Standard 5-day |  | SUP-530 (FS) | SUP-620 (FS)
SUP-620 | Roof finishes and parapet | W36 | task | 6 | 6 | 2027-03-19 | 2027-03-31 |  |  | 381 | 0 | No | No | Standard 5-day |  | SUP-610 (FS) | MS-SUP-END (FS)
MS-SUP-END | Superstructure complete | W30 | finish_milestone | 0 | 0 | 2027-03-31 | 2027-03-31 |  |  | 381 | 0 | No | No | Standard 5-day |  | SUP-620 (FS)
ENV-110 | Curtain wall design freeze | W41 | task | 10 | 10 | 2026-11-27 | 2026-12-11 |  |  | 220 | 0 | No | No | Standard 5-day |  | SUP-160 (FS) | ENV-120 (FS)
ENV-120 | Curtain wall fabrication | W41 | task | 45 | 45 | 2026-12-11 | 2027-02-17 |  |  | 220 | 0 | No | No | Standard 5-day |  | ENV-110 (FS) | ENV-130 (FS)
ENV-130 | Curtain wall logistics & site delivery | W41 | task | 5 | 5 | 2027-02-17 | 2027-02-24 |  |  | 220 | 0 | No | No | Standard 5-day |  | ENV-120 (FS) | ENV-140 (FS)
ENV-140 | Curtain wall install North elevation | W41 | task | 15 | 15 | 2027-03-17 | 2027-04-09 |  |  | 205 | 0 | No | No | Standard 5-day |  | ENV-130 (FS), SUP-530 (FS) | ENV-150 (FS), ENV-210 (FS)
ENV-150 | Curtain wall install East elevation | W41 | task | 15 | 15 | 2027-04-09 | 2027-04-30 |  |  | 205 | 0 | No | No | Standard 5-day |  | ENV-140 (FS) | ENV-160 (FS)
ENV-160 | Curtain wall install South elevation | W41 | task | 15 | 15 | 2027-04-30 | 2027-05-24 |  |  | 205 | 0 | No | No | Standard 5-day |  | ENV-150 (FS) | ENV-170 (FS)
ENV-170 | Curtain wall install West elevation | W41 | task | 15 | 15 | 2027-05-24 | 2027-06-14 |  |  | 205 | 0 | No | No | Standard 5-day |  | ENV-160 (FS) | ENV-180 (FS), ENV-320 (FS)
ENV-180 | Curtain wall snagging | W41 | task | 8 | 8 | 2027-06-14 | 2027-06-24 |  |  | 317 | 0 | No | No | Standard 5-day |  | ENV-170 (FS) | ENV-310 (FS)
ENV-210 | Cladding survey and setting-out | W42 | task | 5 | 5 | 2027-03-17 | 2027-03-24 |  |  | 221 | 0 | No | No | Standard 5-day |  | ENV-140 (FS) | ENV-220 (SS+5d)
ENV-220 | Cladding North elevation | W42 | task | 14 | 14 | 2027-03-24 | 2027-04-15 |  |  | 221 | 0 | No | No | Standard 5-day |  | ENV-210 (SS+5d) | ENV-230 (FS)
ENV-230 | Cladding East elevation | W42 | task | 14 | 14 | 2027-04-15 | 2027-05-06 |  |  | 221 | 0 | No | No | Standard 5-day |  | ENV-220 (FS) | ENV-240 (FS)
ENV-240 | Cladding South elevation | W42 | task | 14 | 14 | 2027-05-06 | 2027-05-26 |  |  | 221 | 0 | No | No | Standard 5-day |  | ENV-230 (FS) | ENV-250 (FS)
ENV-250 | Cladding West elevation | W42 | task | 14 | 14 | 2027-05-26 | 2027-06-15 |  |  | 221 | 0 | No | No | Standard 5-day |  | ENV-240 (FS) | MS-ENV-END (FS)
ENV-310 | External doors install | W43 | task | 10 | 10 | 2027-06-07 | 2027-06-21 |  |  | 317 | 0 | No | No | Standard 5-day |  | ENV-180 (FS)
ENV-320 | Window install upper floors | W43 | task | 12 | 12 | 2027-05-24 | 2027-06-09 |  |  | 205 | 0 | No | No | Standard 5-day |  | ENV-170 (FS) | ENV-330 (FS)
ENV-330 | Window install lower floors | W43 | task | 12 | 12 | 2027-06-09 | 2027-06-25 |  |  | 205 | 0 | No | No | Standard 5-day |  | ENV-320 (FS) | ENV-340 (FS)
ENV-340 | Glazing and seals | W43 | task | 8 | 8 | 2027-06-25 | 2027-07-07 |  |  | 205 | 0 | No | No | Standard 5-day |  | ENV-330 (FS) | MS-ENV-END (FS)
MS-ENV-END | Envelope watertight | W40 | finish_milestone | 0 | 0 | 2027-07-07 | 2027-07-07 |  |  | 205 | 0 | No | No | Standard 5-day |  | ENV-250 (FS), ENV-340 (FS) | EXT-110 (FS)
MEP-110 | Main intake and switchgear | W51 | task | 12 | 12 | 2027-02-24 | 2027-03-12 |  |  | 48 | 0 | No | No | Standard 5-day |  | MS-SUB-END (FS) | MEP-120 (FS)
MEP-120 | Electrical containment L1-L3 | W51 | task | 18 | 18 | 2027-03-12 | 2027-04-09 |  |  | 10 | 0 | No | No | Standard 5-day |  | MEP-110 (FS), SUP-360 (FS) | MEP-130 (FS), MEP-140 (FS)
MEP-130 | Electrical containment L4-L6 | W51 | task | 18 | 18 | 2027-04-09 | 2027-05-06 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | MEP-120 (FS), SUP-460 (FS) | MEP-140 (FS)
MEP-140 | Cable pulling L1-L3 | W51 | task | 20 | 20 | 2027-05-06 | 2027-06-03 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | MEP-120 (FS), MEP-130 (FS) | MEP-150 (FS)
MEP-150 | Cable pulling L4-L6 | W51 | task | 20 | 20 | 2027-06-03 | 2027-07-01 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | MEP-140 (FS) | MEP-160 (FS)
MEP-160 | Distribution boards | W51 | task | 12 | 12 | 2027-07-01 | 2027-07-19 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | MEP-150 (FS) | MEP-170 (FS)
MEP-170 | Lighting wiring rough-in | W51 | task | 18 | 18 | 2027-07-19 | 2027-08-12 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | MEP-160 (FS) | MEP-180 (FS)
MEP-180 | Power outlet rough-in | W51 | task | 18 | 18 | 2027-08-12 | 2027-09-08 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | MEP-170 (FS) | FIT-110 (FS), MS-MEP-END (FS)
MEP-210 | Plant room frame and pads | W52 | task | 15 | 15 | 2027-02-10 | 2027-03-03 |  |  | 20 | 0 | No | No | Standard 5-day |  | SUP-160 (FS) | MEP-220 (FS)
MEP-220 | AHUs delivery and install | W52 | task | 20 | 20 | 2027-03-03 | 2027-04-02 |  |  | 20 | 0 | No | No | Standard 5-day |  | MEP-210 (FS) | MEP-230 (FS)
MEP-230 | Chillers install | W52 | task | 15 | 15 | 2027-04-02 | 2027-04-23 |  |  | 20 | 0 | No | No | Standard 5-day |  | MEP-220 (FS) | MEP-240 (FS)
MEP-240 | Risers L1-L6 | W52 | task | 25 | 25 | 2027-04-23 | 2027-05-31 |  |  | 20 | 0 | No | No | Standard 5-day |  | MEP-230 (FS) | MEP-250 (FS)
MEP-250 | Floor ductwork L1-L3 | W52 | task | 25 | 25 | 2027-05-31 | 2027-07-05 |  |  | 20 | 0 | No | No | Standard 5-day |  | MEP-240 (FS) | MEP-260 (FS)
MEP-260 | Floor ductwork L4-L6 | W52 | task | 25 | 25 | 2027-07-05 | 2027-08-09 |  |  | 20 | 0 | No | No | Standard 5-day |  | MEP-250 (FS) | MEP-270 (FS)
MEP-270 | VRF system install | W52 | task | 18 | 18 | 2027-08-09 | 2027-09-03 |  |  | 20 | 0 | No | No | Standard 5-day |  | MEP-260 (FS) | MEP-280 (FS)
MEP-280 | Insulation and labelling | W52 | task | 12 | 12 | 2027-09-03 | 2027-09-21 |  |  | 20 | 0 | No | No | Standard 5-day |  | MEP-270 (FS) | CMS-110 (FS), FIT-160 (FS+15d), MS-MEP-END (FS)
MEP-310 | Below-slab drainage | W53 | task | 15 | 15 | 2026-07-30 | 2026-08-20 |  |  | 544 | 0 | No | No | Standard 5-day |  | SUB-310 (FS)
MEP-320 | Riser plumbing | W53 | task | 20 | 20 | 2027-04-09 | 2027-05-10 |  |  | 355 | 0 | No | No | Standard 5-day |  | SUP-160 (FS) | MEP-330 (FS)
MEP-330 | Floor plumbing L1-L3 | W53 | task | 22 | 22 | 2027-05-10 | 2027-06-09 |  |  | 355 | 0 | No | No | Standard 5-day |  | MEP-320 (FS) | MEP-340 (FS)
MEP-340 | Floor plumbing L4-L6 | W53 | task | 22 | 22 | 2027-06-09 | 2027-07-09 |  |  | 355 | 0 | No | No | Standard 5-day |  | MEP-330 (FS) | MEP-350 (FS)
MEP-350 | Sprinkler mains | W53 | task | 25 | 25 | 2027-05-24 | 2027-06-28 |  |  | 355 | 0 | No | No | Standard 5-day |  | MEP-340 (FS) | MEP-360 (FS)
MEP-360 | Sprinkler floor distribution | W53 | task | 25 | 25 | 2027-07-09 | 2027-08-13 |  |  | 355 | 0 | No | No | Standard 5-day |  | MEP-350 (FS) | MS-MEP-END (FS)
MS-MEP-END | MEP rough-in complete | W50 | finish_milestone | 0 | 0 | 2027-09-21 | 2027-09-21 |  |  | 313 | 0 | No | No | Standard 5-day |  | MEP-180 (FS), MEP-280 (FS), MEP-360 (FS)
FIT-110 | Stud partition L1 | W61 | task | 12 | 12 | 2027-08-16 | 2027-09-02 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | MEP-180 (FS) | FIT-120 (SS+4d)
FIT-120 | Stud partition L2 | W61 | task | 12 | 12 | 2027-08-24 | 2027-09-10 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-110 (SS+4d) | FIT-130 (SS+4d)
FIT-130 | Stud partition L3 | W61 | task | 12 | 12 | 2027-09-02 | 2027-09-20 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-120 (SS+4d) | FIT-140 (SS+4d)
FIT-140 | Stud partition L4 | W61 | task | 12 | 12 | 2027-09-10 | 2027-09-28 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-130 (SS+4d) | FIT-150 (SS+4d)
FIT-150 | Stud partition L5-L6 | W61 | task | 18 | 18 | 2027-09-20 | 2027-10-14 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-140 (SS+4d) | FIT-160 (FS)
FIT-160 | Suspended ceilings L1-L3 | W61 | task | 25 | 25 | 2027-09-20 | 2027-10-25 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-150 (FS), MEP-280 (FS+15d) | FIT-170 (FS)
FIT-170 | Suspended ceilings L4-L6 | W61 | task | 25 | 25 | 2027-10-14 | 2027-11-18 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-160 (FS) | FIT-180 (FS)
FIT-180 | Ceiling integration MEP | W61 | task | 12 | 12 | 2027-10-25 | 2027-11-10 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-170 (FS) | CMS-110 (FS), FIT-210 (FS)
FIT-210 | Plastering L1-L3 | W62 | task | 20 | 20 | 2027-10-06 | 2027-11-03 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-180 (FS) | FIT-220 (FS), FIT-230 (FS)
FIT-220 | Plastering L4-L6 | W62 | task | 20 | 20 | 2027-11-03 | 2027-12-01 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-210 (FS) | FIT-240 (FS)
FIT-230 | Painting L1-L3 | W62 | task | 18 | 18 | 2027-11-03 | 2027-11-29 |  |  | 157 | 0 | No | No | Standard 5-day |  | FIT-210 (FS) | FIT-250 (FS)
FIT-240 | Painting L4-L6 | W62 | task | 18 | 18 | 2027-12-01 | 2027-12-29 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-220 (FS) | FIT-260 (FS)
FIT-250 | Floor finishes L1-L3 | W62 | task | 22 | 22 | 2027-11-29 | 2027-12-31 |  |  | 157 | 0 | No | No | Standard 5-day |  | FIT-230 (FS)
FIT-260 | Floor finishes L4-L6 | W62 | task | 22 | 22 | 2027-12-29 | 2028-01-28 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-240 (FS) | FIT-270 (FS), FIT-310 (FS)
FIT-270 | Wall finishes specialty zones | W62 | task | 15 | 15 | 2028-01-06 | 2028-01-27 |  |  | 63 | 0 | No | No | Standard 5-day |  | FIT-260 (FS) | FIT-280 (FS)
FIT-280 | Decoration handover | W62 | task | 8 | 8 | 2028-01-27 | 2028-02-08 |  |  | 63 | 0 | No | No | Standard 5-day |  | FIT-270 (FS) | MS-FIT-END (FS)
FIT-310 | Reception joinery | W63 | task | 15 | 15 | 2028-01-06 | 2028-01-27 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-260 (FS) | FIT-320 (FS)
FIT-320 | Toilet vanity install | W63 | task | 18 | 18 | 2028-01-06 | 2028-02-01 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-310 (FS) | FIT-330 (FS)
FIT-330 | Tea-point joinery | W63 | task | 12 | 12 | 2028-01-13 | 2028-01-31 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-320 (FS) | FIT-340 (FS)
FIT-340 | Meeting room joinery | W63 | task | 18 | 18 | 2028-01-20 | 2028-02-15 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-330 (FS) | FIT-350 (FS)
FIT-350 | Built-in storage and fittings | W63 | task | 15 | 15 | 2028-02-03 | 2028-02-24 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-340 (FS) | FIT-360 (FS)
FIT-360 | Final joinery snagging | W63 | task | 8 | 8 | 2028-02-24 | 2028-03-07 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-350 (FS) | MS-FIT-END (FS)
MS-FIT-END | Fit-out complete | W60 | finish_milestone | 0 | 0 | 2028-03-07 | 2028-03-07 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | FIT-280 (FS), FIT-360 (FS) | CMS-210 (FS)
EXT-110 | External drainage | W71 | task | 18 | 18 | 2027-08-31 | 2027-09-24 |  |  | 205 | 0 | No | No | Standard 5-day |  | MS-ENV-END (FS) | EXT-120 (FS)
EXT-120 | Sub-base preparation | W71 | task | 12 | 12 | 2027-09-24 | 2027-10-12 |  |  | 205 | 0 | No | No | Standard 5-day |  | EXT-110 (FS) | EXT-130 (FS)
EXT-130 | Tarmac surfacing | W71 | task | 10 | 10 | 2027-10-12 | 2027-10-26 |  |  | 205 | 0 | No | No | Standard 5-day |  | EXT-120 (FS) | EXT-140 (FS)
EXT-140 | Line marking and signage | W71 | task | 6 | 6 | 2027-10-26 | 2027-11-03 |  |  | 205 | 0 | No | No | Standard 5-day |  | EXT-130 (FS) | EXT-210 (FS)
EXT-210 | Soft landscape preparation | W72 | task | 12 | 12 | 2027-10-26 | 2027-11-11 |  |  | 205 | 0 | No | No | Standard 5-day |  | EXT-140 (FS) | EXT-220 (FS)
EXT-220 | Planting and turf | W72 | task | 15 | 15 | 2027-11-11 | 2027-12-02 |  |  | 205 | 0 | No | No | Standard 5-day |  | EXT-210 (FS) | EXT-230 (FS)
EXT-230 | Hard landscape features | W72 | task | 10 | 10 | 2027-12-02 | 2027-12-16 |  |  | 205 | 0 | No | No | Standard 5-day |  | EXT-220 (FS) | MS-EXT-END (FS)
EXT-310 | Boundary fencing | W73 | task | 12 | 12 | 2027-11-23 | 2027-12-09 |  |  | 653 | 0 | No | No | Standard 5-day |  |  | EXT-320 (FS)
EXT-320 | Gates and access controls | W73 | task | 8 | 8 | 2027-12-09 | 2027-12-21 |  |  | 653 | 0 | No | No | Standard 5-day |  | EXT-310 (FS) | MS-EXT-END (FS)
MS-EXT-END | External works complete | W70 | finish_milestone | 0 | 0 | 2027-12-21 | 2027-12-21 |  |  | 205 | 0 | No | No | Standard 5-day |  | EXT-230 (FS), EXT-320 (FS) | CMS-310 (FS)
CMS-110 | Mechanical commissioning | W81 | task | 18 | 18 | 2028-02-17 | 2028-03-14 |  |  | 113 | 0 | No | No | Standard 5-day |  | FIT-180 (FS), MEP-280 (FS) | CMS-120 (SS+8d)
CMS-120 | Electrical commissioning | W81 | task | 15 | 15 | 2028-02-29 | 2028-03-21 |  |  | 113 | 0 | No | No | Standard 5-day |  | CMS-110 (SS+8d) | CMS-130 (FS)
CMS-130 | BMS integration and tuning | W81 | task | 12 | 12 | 2028-03-14 | 2028-03-30 |  |  | 113 | 0 | No | No | Standard 5-day |  | CMS-120 (FS) | CMS-140 (FS)
CMS-140 | Fire and life-safety witness tests | W81 | task | 10 | 10 | 2028-03-28 | 2028-04-11 |  |  | 113 | 0 | No | No | Standard 5-day |  | CMS-130 (FS) | CMS-150 (FS)
CMS-150 | Air leakage and BREEAM tests | W81 | task | 8 | 8 | 2028-04-06 | 2028-04-18 |  |  | 113 | 0 | No | No | Standard 5-day |  | CMS-140 (FS) | CMS-210 (FS)
CMS-210 | Client walkthrough and snag list | W82 | task | 5 | 5 | 2028-04-18 | 2028-04-25 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | CMS-150 (FS), MS-FIT-END (FS) | CMS-220 (FS)
CMS-220 | Major snags rectification | W82 | task | 15 | 15 | 2028-04-25 | 2028-05-16 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | CMS-210 (FS) | CMS-230 (FS)
CMS-230 | Minor snags rectification | W82 | task | 12 | 12 | 2028-05-04 | 2028-05-22 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | CMS-220 (FS) | CMS-240 (FS)
CMS-240 | Final inspection | W82 | task | 4 | 4 | 2028-05-16 | 2028-05-22 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | CMS-230 (FS) | CMS-310 (FS)
CMS-310 | Building handover documentation | W83 | task | 8 | 8 | 2028-05-18 | 2028-05-30 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | CMS-240 (FS), MS-EXT-END (FS) | CMS-320 (FS)
CMS-320 | O&M manuals issued | W83 | task | 4 | 4 | 2028-05-30 | 2028-06-05 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | CMS-310 (FS) | CMS-330 (FS)
CMS-330 | Soft landings start | W83 | task | 3 | 3 | 2028-06-05 | 2028-06-08 |  |  | 0 | 0 | Yes | No | Standard 5-day |  | CMS-320 (FS) | MS-PC (FS)
MS-PC | Practical Completion | W83 | finish_milestone | 0 | 0 | 2028-06-08 | 2028-06-08 |  |  | 0 | 0 | Yes | No | Standard 5-day | FNLT | CMS-330 (FS)

## Float Paths
Rank | Float (wd) | Activity count | Divergent count | Envelope start | Envelope finish | Driving activity ID | Driving activity name | Branches from rank | Branches at activity | Activity sequence
1 | 0 | 68 | 68 | 2026-01-05 | 2028-06-08 | MS-START | Project Start |  |  | MS-START, PRE-110, PRE-120, PRE-130, PRE-140, SUB-110, SUB-210, SUB-220, SUB-230, SUB-240, SUB-250, SUB-310, SUB-320, SUB-330, SUB-340, SUB-410, SUB-420, SUB-430, SUB-440, MS-SUB-END, SUP-110, SUP-120, SUP-130, SUP-140, SUP-150, SUP-160, SUP-210, SUP-220, SUP-230, SUP-240, SUP-250, SUP-260, SUP-440, SUP-450, SUP-460, MEP-130, MEP-140, MEP-150, MEP-160, MEP-170, MEP-180, FIT-110, FIT-120, FIT-130, FIT-140, FIT-150, FIT-160, FIT-170, FIT-180, FIT-210, FIT-220, FIT-240, FIT-260, FIT-310, FIT-320, FIT-330, FIT-340, FIT-350, FIT-360, MS-FIT-END, CMS-210, CMS-220, CMS-230, CMS-240, CMS-310, CMS-320, CMS-330, MS-PC
2 | 7 | 67 | 4 | 2026-02-09 | 2028-06-08 | PRE-210 | Site mobilisation | 1 | SUB-110 | PRE-210, PRE-220, PRE-240, PRE-250, SUB-110, SUB-210, SUB-220, SUB-230, SUB-240, SUB-250, SUB-310, SUB-320, SUB-330, SUB-340, SUB-410, SUB-420, SUB-430, SUB-440, MS-SUB-END, SUP-110, SUP-120, SUP-130, SUP-140, SUP-150, SUP-160, SUP-210, SUP-220, SUP-230, SUP-240, SUP-250, SUP-260, SUP-440, SUP-450, SUP-460, MEP-130, MEP-140, MEP-150, MEP-160, MEP-170, MEP-180, FIT-110, FIT-120, FIT-130, FIT-140, FIT-150, FIT-160, FIT-170, FIT-180, FIT-210, FIT-220, FIT-240, FIT-260, FIT-310, FIT-320, FIT-330, FIT-340, FIT-350, FIT-360, MS-FIT-END, CMS-210, CMS-220, CMS-230, CMS-240, CMS-310, CMS-320, CMS-330, MS-PC
3 | 10 | 37 | 4 | 2026-11-06 | 2028-06-08 | SUP-340 | Slab L2 formwork | 1 | MEP-130 | SUP-340, SUP-350, SUP-360, MEP-120, MEP-130, MEP-140, MEP-150, MEP-160, MEP-170, MEP-180, FIT-110, FIT-120, FIT-130, FIT-140, FIT-150, FIT-160, FIT-170, FIT-180, FIT-210, FIT-220, FIT-240, FIT-260, FIT-310, FIT-320, FIT-330, FIT-340, FIT-350, FIT-360, MS-FIT-END, CMS-210, CMS-220, CMS-230, CMS-240, CMS-310, CMS-320, CMS-330, MS-PC
4 | 20 | 30 | 8 | 2027-02-10 | 2028-06-08 | MEP-210 | Plant room frame and pads | 1 | FIT-160 | MEP-210, MEP-220, MEP-230, MEP-240, MEP-250, MEP-260, MEP-270, MEP-280, FIT-160, FIT-170, FIT-180, FIT-210, FIT-220, FIT-240, FIT-260, FIT-310, FIT-320, FIT-330, FIT-340, FIT-350, FIT-360, MS-FIT-END, CMS-210, CMS-220, CMS-230, CMS-240, CMS-310, CMS-320, CMS-330, MS-PC

## Constraints
Activity ID | Activity Name | WBS | Constraint Type | Constraint Date | Hard (DCMA §5) | Complete | Total Float (wd)
MS-PC | Practical Completion | W83 | FNLT | 2028-09-12 | No | No | 0
MS-START | Project Start | W10 | SO | 2026-01-05 | No | No | 0
PRE-140 | Building control approval | W11 | SNLT | 2026-03-23 | No | No | 0

## Lags
Predecessor ID | Predecessor Name | Successor ID | Successor Name | Type | Lag (wd)
CMS-110 | Mechanical commissioning | CMS-120 | Electrical commissioning | SS | 8
ENV-210 | Cladding survey and setting-out | ENV-220 | Cladding North elevation | SS | 5
FIT-110 | Stud partition L1 | FIT-120 | Stud partition L2 | SS | 4
FIT-120 | Stud partition L2 | FIT-130 | Stud partition L3 | SS | 4
FIT-130 | Stud partition L3 | FIT-140 | Stud partition L4 | SS | 4
FIT-140 | Stud partition L4 | FIT-150 | Stud partition L5-L6 | SS | 4
MEP-280 | Insulation and labelling | FIT-160 | Suspended ceilings L1-L3 | FS | 15
PRE-110 | Submit planning permission application | PRE-210 | Site mobilisation | FS | 20
SUB-110 | Bulk excavation Zone A | SUB-120 | Bulk excavation Zone B | SS | 5

## Long-duration activities
Activity ID | Activity Name | WBS | Duration (wd) | Remaining Duration (wd) | Planned Start | Planned Finish | Total Float (wd) | Critical | Calendar
ENV-120 | Curtain wall fabrication | W41 | 45 | 45 | 2026-12-11 | 2027-02-17 | 220 | No | 1

## Float over threshold
Activity ID | Activity Name | WBS | Duration (wd) | Remaining Duration (wd) | Planned Start | Planned Finish | Total Float (wd) | Critical | Calendar
PRE-230 | Welfare cabins and offices | W12 | 7 | 7 | 2026-02-19 | 2026-03-02 | 648 | No | 1
SUP-310 | Slab L1 formwork | W33 | 8 | 8 | 2026-10-13 | 2026-10-23 | 461 | No | 1
SUP-320 | Slab L1 reinforcement | W33 | 8 | 8 | 2026-10-23 | 2026-11-04 | 461 | No | 1
SUP-330 | Slab L1 pour | W33 | 6 | 6 | 2026-11-04 | 2026-11-12 | 461 | No | 1
SUP-410 | Slab L3 formwork | W34 | 8 | 8 | 2026-11-30 | 2026-12-10 | 425 | No | 1
SUP-420 | Slab L3 reinforcement | W34 | 8 | 8 | 2026-12-10 | 2026-12-22 | 425 | No | 1
SUP-430 | Slab L3 pour | W34 | 6 | 6 | 2026-12-22 | 2027-01-04 | 425 | No | 1
SUP-510 | Roof slab formwork | W35 | 10 | 10 | 2027-02-03 | 2027-02-17 | 206 | No | 1
SUP-520 | Roof slab reinforcement | W35 | 8 | 8 | 2027-02-17 | 2027-03-01 | 206 | No | 1
SUP-530 | Roof slab pour | W35 | 6 | 6 | 2027-03-01 | 2027-03-09 | 206 | No | 1
SUP-610 | Roof waterproofing membrane | W36 | 8 | 8 | 2027-03-09 | 2027-03-19 | 381 | No | 1
SUP-620 | Roof finishes and parapet | W36 | 6 | 6 | 2027-03-19 | 2027-03-31 | 381 | No | 1
MS-SUP-END | Superstructure complete | W30 | 0 | 0 | 2027-03-31 | 2027-03-31 | 381 | No | 1
ENV-110 | Curtain wall design freeze | W41 | 10 | 10 | 2026-11-27 | 2026-12-11 | 220 | No | 1
ENV-120 | Curtain wall fabrication | W41 | 45 | 45 | 2026-12-11 | 2027-02-17 | 220 | No | 1
ENV-130 | Curtain wall logistics & site delivery | W41 | 5 | 5 | 2027-02-17 | 2027-02-24 | 220 | No | 1
ENV-140 | Curtain wall install North elevation | W41 | 15 | 15 | 2027-03-17 | 2027-04-09 | 205 | No | 1
ENV-150 | Curtain wall install East elevation | W41 | 15 | 15 | 2027-04-09 | 2027-04-30 | 205 | No | 1
ENV-160 | Curtain wall install South elevation | W41 | 15 | 15 | 2027-04-30 | 2027-05-24 | 205 | No | 1
ENV-170 | Curtain wall install West elevation | W41 | 15 | 15 | 2027-05-24 | 2027-06-14 | 205 | No | 1
ENV-180 | Curtain wall snagging | W41 | 8 | 8 | 2027-06-14 | 2027-06-24 | 317 | No | 1
ENV-210 | Cladding survey and setting-out | W42 | 5 | 5 | 2027-03-17 | 2027-03-24 | 221 | No | 1
ENV-220 | Cladding North elevation | W42 | 14 | 14 | 2027-03-24 | 2027-04-15 | 221 | No | 1
ENV-230 | Cladding East elevation | W42 | 14 | 14 | 2027-04-15 | 2027-05-06 | 221 | No | 1
ENV-240 | Cladding South elevation | W42 | 14 | 14 | 2027-05-06 | 2027-05-26 | 221 | No | 1
ENV-250 | Cladding West elevation | W42 | 14 | 14 | 2027-05-26 | 2027-06-15 | 221 | No | 1
ENV-310 | External doors install | W43 | 10 | 10 | 2027-06-07 | 2027-06-21 | 317 | No | 1
ENV-320 | Window install upper floors | W43 | 12 | 12 | 2027-05-24 | 2027-06-09 | 205 | No | 1
ENV-330 | Window install lower floors | W43 | 12 | 12 | 2027-06-09 | 2027-06-25 | 205 | No | 1
ENV-340 | Glazing and seals | W43 | 8 | 8 | 2027-06-25 | 2027-07-07 | 205 | No | 1
MS-ENV-END | Envelope watertight | W40 | 0 | 0 | 2027-07-07 | 2027-07-07 | 205 | No | 1
MEP-110 | Main intake and switchgear | W51 | 12 | 12 | 2027-02-24 | 2027-03-12 | 48 | No | 1
MEP-310 | Below-slab drainage | W53 | 15 | 15 | 2026-07-30 | 2026-08-20 | 544 | No | 1
MEP-320 | Riser plumbing | W53 | 20 | 20 | 2027-04-09 | 2027-05-10 | 355 | No | 1
MEP-330 | Floor plumbing L1-L3 | W53 | 22 | 22 | 2027-05-10 | 2027-06-09 | 355 | No | 1
MEP-340 | Floor plumbing L4-L6 | W53 | 22 | 22 | 2027-06-09 | 2027-07-09 | 355 | No | 1
MEP-350 | Sprinkler mains | W53 | 25 | 25 | 2027-05-24 | 2027-06-28 | 355 | No | 1
MEP-360 | Sprinkler floor distribution | W53 | 25 | 25 | 2027-07-09 | 2027-08-13 | 355 | No | 1
MS-MEP-END | MEP rough-in complete | W50 | 0 | 0 | 2027-09-21 | 2027-09-21 | 313 | No | 1
FIT-230 | Painting L1-L3 | W62 | 18 | 18 | 2027-11-03 | 2027-11-29 | 157 | No | 1
FIT-250 | Floor finishes L1-L3 | W62 | 22 | 22 | 2027-11-29 | 2027-12-31 | 157 | No | 1
FIT-270 | Wall finishes specialty zones | W62 | 15 | 15 | 2028-01-06 | 2028-01-27 | 63 | No | 1
FIT-280 | Decoration handover | W62 | 8 | 8 | 2028-01-27 | 2028-02-08 | 63 | No | 1
EXT-110 | External drainage | W71 | 18 | 18 | 2027-08-31 | 2027-09-24 | 205 | No | 1
EXT-120 | Sub-base preparation | W71 | 12 | 12 | 2027-09-24 | 2027-10-12 | 205 | No | 1
EXT-130 | Tarmac surfacing | W71 | 10 | 10 | 2027-10-12 | 2027-10-26 | 205 | No | 1
EXT-140 | Line marking and signage | W71 | 6 | 6 | 2027-10-26 | 2027-11-03 | 205 | No | 1
EXT-210 | Soft landscape preparation | W72 | 12 | 12 | 2027-10-26 | 2027-11-11 | 205 | No | 1
EXT-220 | Planting and turf | W72 | 15 | 15 | 2027-11-11 | 2027-12-02 | 205 | No | 1
EXT-230 | Hard landscape features | W72 | 10 | 10 | 2027-12-02 | 2027-12-16 | 205 | No | 1
EXT-310 | Boundary fencing | W73 | 12 | 12 | 2027-11-23 | 2027-12-09 | 653 | No | 1
EXT-320 | Gates and access controls | W73 | 8 | 8 | 2027-12-09 | 2027-12-21 | 653 | No | 1
MS-EXT-END | External works complete | W70 | 0 | 0 | 2027-12-21 | 2027-12-21 | 205 | No | 1
CMS-110 | Mechanical commissioning | W81 | 18 | 18 | 2028-02-17 | 2028-03-14 | 113 | No | 1
CMS-120 | Electrical commissioning | W81 | 15 | 15 | 2028-02-29 | 2028-03-21 | 113 | No | 1
CMS-130 | BMS integration and tuning | W81 | 12 | 12 | 2028-03-14 | 2028-03-30 | 113 | No | 1
CMS-140 | Fire and life-safety witness tests | W81 | 10 | 10 | 2028-03-28 | 2028-04-11 | 113 | No | 1
CMS-150 | Air leakage and BREEAM tests | W81 | 8 | 8 | 2028-04-06 | 2028-04-18 | 113 | No | 1

## Near-critical activities
Activity ID | Activity Name | WBS | Duration (wd) | Remaining Duration (wd) | Planned Start | Planned Finish | Total Float (wd) | Critical | Calendar
PRE-210 | Site mobilisation | W12 | 8 | 8 | 2026-02-09 | 2026-02-19 | 7 | No | 1
PRE-220 | Site hoarding and access | W12 | 5 | 5 | 2026-02-19 | 2026-02-26 | 7 | No | 1
PRE-240 | Temporary services connection | W12 | 6 | 6 | 2026-02-26 | 2026-03-06 | 7 | No | 1
PRE-250 | Site security and CCTV | W12 | 4 | 4 | 2026-03-06 | 2026-03-12 | 7 | No | 1
SUP-340 | Slab L2 formwork | W33 | 8 | 8 | 2026-11-06 | 2026-11-18 | 10 | No | 1
SUP-350 | Slab L2 reinforcement | W33 | 8 | 8 | 2026-11-18 | 2026-11-30 | 10 | No | 1
SUP-360 | Slab L2 pour | W33 | 6 | 6 | 2026-11-30 | 2026-12-08 | 10 | No | 1
MEP-120 | Electrical containment L1-L3 | W51 | 18 | 18 | 2027-03-12 | 2027-04-09 | 10 | No | 1
MEP-210 | Plant room frame and pads | W52 | 15 | 15 | 2027-02-10 | 2027-03-03 | 20 | No | 1
MEP-220 | AHUs delivery and install | W52 | 20 | 20 | 2027-03-03 | 2027-04-02 | 20 | No | 1
MEP-230 | Chillers install | W52 | 15 | 15 | 2027-04-02 | 2027-04-23 | 20 | No | 1
MEP-240 | Risers L1-L6 | W52 | 25 | 25 | 2027-04-23 | 2027-05-31 | 20 | No | 1
MEP-250 | Floor ductwork L1-L3 | W52 | 25 | 25 | 2027-05-31 | 2027-07-05 | 20 | No | 1
MEP-260 | Floor ductwork L4-L6 | W52 | 25 | 25 | 2027-07-05 | 2027-08-09 | 20 | No | 1
MEP-270 | VRF system install | W52 | 18 | 18 | 2027-08-09 | 2027-09-03 | 20 | No | 1
MEP-280 | Insulation and labelling | W52 | 12 | 12 | 2027-09-03 | 2027-09-21 | 20 | No | 1

## Dangling-logic activities
Activity ID | Activity Name | WBS | Duration (wd) | Remaining Duration (wd) | Planned Start | Planned Finish | Total Float (wd) | Critical | Calendar
PRE-230 | Welfare cabins and offices | W12 | 7 | 7 | 2026-02-19 | 2026-03-02 | 648 | No | 1
SUP-310 | Slab L1 formwork | W33 | 8 | 8 | 2026-10-13 | 2026-10-23 | 461 | No | 1
SUP-320 | Slab L1 reinforcement | W33 | 8 | 8 | 2026-10-23 | 2026-11-04 | 461 | No | 1
SUP-330 | Slab L1 pour | W33 | 6 | 6 | 2026-11-04 | 2026-11-12 | 461 | No | 1
SUP-410 | Slab L3 formwork | W34 | 8 | 8 | 2026-11-30 | 2026-12-10 | 425 | No | 1
SUP-420 | Slab L3 reinforcement | W34 | 8 | 8 | 2026-12-10 | 2026-12-22 | 425 | No | 1
SUP-430 | Slab L3 pour | W34 | 6 | 6 | 2026-12-22 | 2027-01-04 | 425 | No | 1
ENV-180 | Curtain wall snagging | W41 | 8 | 8 | 2027-06-14 | 2027-06-24 | 317 | No | 1
ENV-310 | External doors install | W43 | 10 | 10 | 2027-06-07 | 2027-06-21 | 317 | No | 1
MEP-310 | Below-slab drainage | W53 | 15 | 15 | 2026-07-30 | 2026-08-20 | 544 | No | 1
FIT-230 | Painting L1-L3 | W62 | 18 | 18 | 2027-11-03 | 2027-11-29 | 157 | No | 1
FIT-250 | Floor finishes L1-L3 | W62 | 22 | 22 | 2027-11-29 | 2027-12-31 | 157 | No | 1

## Open ends - no predecessor
Activity ID | Activity Name | WBS | Duration (wd) | Remaining Duration (wd) | Planned Start | Planned Finish | Total Float (wd) | Critical | Calendar
EXT-310 | Boundary fencing | W73 | 12 | 12 | 2027-11-23 | 2027-12-09 | 653 | No | 1

## Open ends - no successor
Activity ID | Activity Name | WBS | Duration (wd) | Remaining Duration (wd) | Planned Start | Planned Finish | Total Float (wd) | Critical | Calendar
PRE-230 | Welfare cabins and offices | W12 | 7 | 7 | 2026-02-19 | 2026-03-02 | 648 | No | 1
SUP-330 | Slab L1 pour | W33 | 6 | 6 | 2026-11-04 | 2026-11-12 | 461 | No | 1
SUP-430 | Slab L3 pour | W34 | 6 | 6 | 2026-12-22 | 2027-01-04 | 425 | No | 1
ENV-310 | External doors install | W43 | 10 | 10 | 2027-06-07 | 2027-06-21 | 317 | No | 1
MEP-310 | Below-slab drainage | W53 | 15 | 15 | 2026-07-30 | 2026-08-20 | 544 | No | 1
FIT-250 | Floor finishes L1-L3 | W62 | 22 | 22 | 2027-11-29 | 2027-12-31 | 157 | No | 1