## Summary
Schedules in series: | 4
Periods analysed: | 3
First schedule: | SL-DEMO
First data date: | 2026-01-05
Latest schedule: | SL-DEMO
Latest data date: | 2026-04-09
Source-file fingerprints:
Update 1 — Schedule ID: | 1
Update 1 — Name: | SL-DEMO
Update 1 — Source format: | xer
Update 1 — Data date: | 2026-01-05
Update 1 — Project finish: | 2028-06-08
Update 2 — Schedule ID: | 1
Update 2 — Name: | SL-DEMO
Update 2 — Source format: | xer
Update 2 — Data date: | 2026-02-04
Update 2 — Project finish: | 2028-06-15
Update 3 — Schedule ID: | 1
Update 3 — Name: | SL-DEMO
Update 3 — Source format: | xer
Update 3 — Data date: | 2026-03-06
Update 3 — Project finish: | 2028-06-29
Update 4 — Schedule ID: | 1
Update 4 — Name: | SL-DEMO
Update 4 — Source format: | xer
Update 4 — Data date: | 2026-04-09
Update 4 — Project finish: | 2028-06-22
Total delay to completion — observed (wd): | 10
Engine-attributed cumulative total (wd): | 17
Cumulative basis note: | Observed = working-day movement of the project finish between the first and latest schedules (authoritative). Pairwise = running sum of per-period engine-attributed delay. Where the two diverge materially, treat the observed figure as authoritative — see PDF methodology section for the explanation.
Total delay events: | 8
Total critical events: | 6
Total added activities: | 1
Total removed activities: | 0
Total concurrent periods: | 0
Total warnings: | 3
Concurrency strategy: | SCL Delay and Disruption Protocol 2nd Edition (true concurrency)

## Per-update Progression
Seq | Schedule name | Data date | Project finish | Observed cum. delay (wd) | Pairwise cum. delay (wd) | Divergence (wd)
1 | SL-DEMO | 2026-01-05 | 2028-06-08 | 0
2 | SL-DEMO | 2026-02-04 | 2028-06-15 | 5 | 5 | 0
3 | SL-DEMO | 2026-03-06 | 2028-06-29 | 15 | 19 | 4
4 | SL-DEMO | 2026-04-09 | 2028-06-22 | 10 | 17 | 7

## Baseline Evolution
Era | Effective from | Baseline finish | Snapshots | Slip within era (wd) | Re-plan reset (wd) | Reset effect | Instruction | Agreed
Original baseline | 2026-01-05 | 2028-06-08 | 2 | 5 | 10 | added time |  | Agreed
Revised programme (EOT award) | 2026-03-06 | 2028-06-29 | 2 | -5 |  |  | AI-014 | Agreed

## Per-period Summary
Period | Baseline | Update | Baseline data date | Update data date | Engine-attributed (wd) | Observed variance (wd) | Delay events | Critical events | Added activities | Removed activities | Concurrent periods | Warnings
P1 | SL-DEMO | SL-DEMO | 2026-01-05 | 2026-02-04 | 5 | 5 | 1 | 1 | 0 | 0 | 0 | 1
P2 | SL-DEMO | SL-DEMO | 2026-02-04 | 2026-03-06 | 14 | 10 | 5 | 4 | 1 | 0 | 0 | 1
P3 | SL-DEMO | SL-DEMO | 2026-03-06 | 2026-04-09 | -2 | -5 | 2 | 1 | 0 | 0 | 0 | 1

## All Delay Events
Period | Event ID | Category | Period start | Period end | Delay (wd) | Impact basis | Isolated contribution (wd) | Contribution note | Critical | Entitlement (prelim.) | Classification rationale | Affected activities | Description
P1 | dur:SUB-110 | duration_change | 2026-03-23 | 2026-04-17 | 5 | Activity-level | 5 |  | Yes | Contractor risk | Description contains 'ncr' — likely Contractor-performance related. Verify against NCRs, progress records, and resource data. | SUB-110 | Activity SUB-110 (Bulk excavation Zone A): duration increased from 12 to 17 working days (+5).
P2 | prg:PRE-130 | progress | 2026-03-02 | 2026-03-06 | 4 | Activity-level | 4 | Progress events use their measured working-days-behind-plan value as the TIA. This is an observational figure, not a modelled injection; the activity's criticality is still gated by the trace. | Yes | Contractor risk | Progress shortfall against the schedule's own current plan — default CONTRACTOR risk. Verify against cause-of-delay records before relying. | PRE-130 | Activity PRE-130 (Building control submission): no recorded finish at the data date (2026-03-06); 4 working day(s) behind the update schedule's own forecast finish of 2026-03-02.
P2 | dur:SUB-210 | duration_change | 2026-04-10 | 2026-04-24 | 6 | Activity-level | 6 |  | Yes | Contractor risk | Description contains 'ncr' — likely Contractor-performance related. Verify against NCRs, progress records, and resource data. | SUB-210 | Activity SUB-210 (Piling rig mobilisation): duration increased from 4 to 10 working days (+6).
P2 | dur:SUB-240 | duration_change | 2026-06-08 | 2026-06-22 | 4 | Activity-level | 4 |  | Yes | Contractor risk | Description contains 'ncr' — likely Contractor-performance related. Verify against NCRs, progress records, and resource data. | SUB-240 | Activity SUB-240 (Pile integrity testing): duration increased from 6 to 10 working days (+4).
P2 | log:SUP-330->SUP-440:added | logic_change | 2027-01-11 | 2027-01-21 | 0 | Topology | 0 |  | Yes | Neutral | Topology change — entitlement depends on who made the change and why. Manual review required; treat as NEUTRAL pending that review. | SUP-330, SUP-440 | Relationship SUP-330 (Slab L1 pour) → SUP-440 (Slab L4 formwork) added (SS with lag +2).
P2 | add:MEP-355 | added_activity | 2027-06-21 | 2027-07-09 | 14 | Scope — upper bound |  |  | No | Not assessed | Added activity with no clear origin signal in the description. Could be a variation (Employer risk) or a contractor-initiated sequencing activity. Requires review against the variation register. | MEP-355 | Activity MEP-355 (Additional fire-water tank install) added — new scope of 14 working day(s). Delay contribution shown is an upper bound; the true impact depends on whether the activity lies serially on the driving path.
P3 | dur:SUP-310 | duration_change | 2026-10-13 | 2026-10-20 | -3 | Activity-level |  |  | No | Neutral | Duration decrease (acceleration) — no delay to classify. | SUP-310 | Activity SUP-310 (Slab L1 formwork): duration decreased from 8 to 5 working days (-3).
P3 | dur:SUP-340 | duration_change | 2026-11-06 | 2026-11-16 | -2 | Activity-level | 0 |  | Yes | Neutral | Duration decrease (acceleration) — no delay to classify. | SUP-340 | Activity SUP-340 (Slab L2 formwork): duration decreased from 8 to 6 working days (-2).

## All Scope Changes
Period | Change | Activity ID | Activity Name | WBS | Duration (wd) | Planned Start | Planned Finish
P2 | Added | MEP-355 | Additional fire-water tank install | W53 | 14 | 2027-06-21 | 2027-07-09

## All Concurrent Periods
Period | Window start | Window end | Overlapping events | Net impact (wd) | Absorbed (wd)

## All Warnings
Period | Severity | Code | Title | Description
P1 | critical | critical_path_divergence | Traced critical path differs from stored flag on 60 activities | An independent forward/backward pass on the update schedule produced a different critical-path set to the file's stored Activity.is_critical flags on 60 activities. Common causes: stale total-float values (schedule not recalculated after the last edit), retained-logic vs progress-override calculation mode, or constraint-driven criticality the V1 trace does not model. The engine used the traced path for every delay attribution downstream of this section — divergences therefore propagate into the delay register, the criticality flags on specific events, and the isolated contribution figures. Review the divergence before relying on the numbers.
P2 | critical | critical_path_divergence | Traced critical path differs from stored flag on 68 activities | An independent forward/backward pass on the update schedule produced a different critical-path set to the file's stored Activity.is_critical flags on 68 activities. Common causes: stale total-float values (schedule not recalculated after the last edit), retained-logic vs progress-override calculation mode, or constraint-driven criticality the V1 trace does not model. The engine used the traced path for every delay attribution downstream of this section — divergences therefore propagate into the delay register, the criticality flags on specific events, and the isolated contribution figures. Review the divergence before relying on the numbers.
P3 | critical | critical_path_divergence | Traced critical path differs from stored flag on 68 activities | An independent forward/backward pass on the update schedule produced a different critical-path set to the file's stored Activity.is_critical flags on 68 activities. Common causes: stale total-float values (schedule not recalculated after the last edit), retained-logic vs progress-override calculation mode, or constraint-driven criticality the V1 trace does not model. The engine used the traced path for every delay attribution downstream of this section — divergences therefore propagate into the delay register, the criticality flags on specific events, and the isolated contribution figures. Review the divergence before relying on the numbers.

## All Concealed Slip
Period | Activity ID | Activity Name | Shaved field | Submitted (wd) | Restored to (wd) | Shaved (wd) | Capped

## All Update Integrity
Period | Activity ID | Activity Name | Actual field | First reported | Revised to | Shift (cal days)

## All CP Stability
Period | Activity ID | Activity Name | Forecast finish (prior) | Forecast finish (current) | Shift (cal days)

## Forecast Backtest
Forecast data date | Forecast finish | Reference finish | Reference type | Error (cal days) | Lead (cal days)